## Change required to the tails
T_ID | RNO | C_ID | ProgressPercentage | TileName | Change tile name to: | Conditions | Condition/format change to: | Future
1 | 4769 | 1 | 11 | Delayed DOS Start |  | DOS forecast STAR - DOS baseline START >0 | 1.Baseline column before forecast
2 | 4837 | 1 | 12 | Delayed DOS Finish |  | DOS forecast FINISH - DOS baseline FINISH >0
3 | 0 | 1 | 0 | Delayed Departure Port |  | ATD – ETD >0
4 | 0 | 1 | 0 | Delayed Arrival Port |  | ATD – ETA >0
5 | 6245 | 1 | 30 | Delayed Contract Date | Delayed Start Manufacturing | Man. FAT Contract Date - Man. Start Contract Date>0. | 1.Man.Start Forecast/Actual - Man. Start Contract Date > 0 2.Baseline columns must be before the actual forecast
6 | 6584 | 1 | 31 | Delayed Forecast/Actual | Delayed FAT Date | Man. FAT Forecast/Actual - Man. Forecast/Actual >0 | 1.Man. FAT Forecast/Actual - Man.FAT Contract Date >0 2.Baseline columns must be before the actual forecast
7 | 3649 | 1 | 18 | Delayed Final/Pre Ship |  | Man. Final/Pre ship. Inst Forecast/Actual - Man. Final/Pre ship. Insp. Contract Date >0 | 1.Man. Final/Pre ship. Inst Forecast/Actual - Man. Final/Pre ship. Insp. Contract Date >0. 2.Baseline columns must be before the actual forecast
8 | 217 | 1 | 9 | Qty MR <> Qty DP |  | Qty MR <> Qty DP |  | Link to the object page
9 | 22 | 1 | 2 | Qty MR <> Qty BOM |  | Qty MR <> Qty BOM |  | Link to the object page
10 | 219 | 1 | 27 | Qty DP <> Qty BOM |  | Qty DP <> Qty BOM |  | Link to the object page
11 | 2200 | 1 | 44 | Qty MR <> Qty DP |  | Qty MR <> Qty DP | 1.Insert the column Sub-item after the object code | Link to the object page
12 | 1 | 1 | 0 | Qty MR <> Qty BOM |  | Qty MR <> Qty BOM |  | Link to the object page
13 | 114 | 2 | 0 | EXW > ETD | EXW/ETD Date Sequence | EXW > ETD | 1.Insert the column Sub-item after the object code
14 | 6 | 2 | 0 | ETD > ETA | Date Sequence ETD/ETA | EXW > ETD | 1.Insert the column Sub-item after the object code
15 | 124 | 2 | 3 | ETA > DOS Baseline Start and DOS Act/For Start | ETA > DOS Baseline Start and DOS Act/For Start Date Sequence | ETA > DOS Baseline START and DOS Act/For START | 1.Insert the column Sub-item after the object code
16 | 18 | 2 | 0 | DOS Baseline Start > DOS Baseline Finish | DOS Baseline Start > DOS Baseline Finish Date Sequence | DOS Baseline START > DOS Baseline FINISH | 1.Insert the column Sub-item after the object code
17 | 34 | 2 | 0 | DOS Act/For Start > DOS Act/For Finish | DOS Act/For Start > DOS Act/For Finish Date Sequence | DOS Act/For START > DOS Act/For FINISH | 1.Insert the column Sub-item after the object code
18 | 167 | 2 | 2 | Man.Start Contract Date > Man.FAT Contract Date | Man.Start Contract Date > Man.FAT Contract Date Date Sequence | Man.Start Contract Date > Man.FAT Contract Date | 1.Insert the column Sub-item after the object code
19 | 96 | 2 | 1 | Man.Start Forecast/Actual > Man.FAT Forecast/Actual | Man.Start Forecast/Actual > Man.FAT Forecast/Actual Date Sequence | Man.Start Forecast/Actual > Man.FAT Forecast/Actual | 1.Insert the column Sub-item after the object code
20 | 107 | 2 | 1 | Man.Start Contract Date > Man.Final/Pre-ship Insp. Cont. Date | Man.Start Contract Date > Man.Final/Pre-ship Insp. Cont. Date Date Sequence | Man.Start Contract Date > Man.Final/Pre-ship Insp. Cont. Date | 1.Insert the column Sub-item after the object code
21 | 105 | 2 | 1 | Man.Start Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual | Man.Start Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual Date Sequence | Man.Start Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual | 1.Insert the column Sub-item after the object code
22 | 107 | 2 | 1 | Man.FAT Contract Date > Man.Final/Pre-ship Insp. Cont. Date | Man.FAT Contract Date > Man.Final/Pre-ship Insp. Cont. Date Date Sequence | Man.FAT Contract Date > Man.Final/Pre-ship Insp. Cont. Date | 1.Insert the column Sub-item after the object code
23 | 127 | 2 | 1 | Man.FAT Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual | Man.FAT Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual Date Sequence | Man.FAT Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual | 1.Insert the column Sub-item after the object code
24 | 3549 | 2 | 73 | EXW <> Man.Final/Pre-ship Insp. Forecast/Actual |  | EXW <> Man.Final/Pre-ship Insp. Forecast/Actual | 1.Insert the column Sub-item after the object code
25 | 1824 | 3 | 25 | Manufacturing Status |  | Man.Final/Pre-ship Insp. Forecast/Actual < Today e flg “Working Status” non impostato. | 1.Insert the column Sub-item after the object code
26 | 2219 | 3 | 19 | Delivered Status |  | DOS Act/For FINISH < Today e flg “Delivered” non impostato | 1.Insert the column Sub-item after the object code
27 | 860 | 3 | 12 | Date Missing In MR
28 | 10299 | 3 | 82 | Date Missing In DP |  | Insert the Sub-item

## New TILES loading approach
T_ID | RNO | C_ID | ProgressPercentage | TileName | Conditions | Overall | Static
1 | 4769 | 1 | 11 | Delayed DOS Start | DOS forecast STAR - DOS baseline START >0
2 | 4837 | 1 | 12 | Delayed DOS Finish | DOS forecast FINISH - DOS baseline FINISH >0
3 | 0 | 1 | 0 | Delayed Departure Port | ATD – ETD >0
4 | 0 | 1 | 0 | Delayed Arrival Port | ATD – ETA >0
5 | 6245 | 1 | 30 | Delayed Contract Date | Man. FAT Contract Date - Man. Start Contract Date>0.
6 | 6584 | 1 | 31 | Delayed Forecast/Actual | Man. FAT Forecast/Actual - Man. Forecast/Actual >0
7 | 3656 | 1 | 18 | Delayed Final/Pre Ship | Man. Final/Pre ship. Inst Forecast/Actual - Man. Final/Pre ship. Insp. Contract Date >0
8 | 217 | 1 | 9 | Qty MR <> Qty DP | Qty MR <> Qty DP
9 | 22 | 1 | 2 | Qty MR <> Qty BOM | Qty MR <> Qty BOM
10 | 219 | 1 | 27 | Qty DP <> Qty BOM | Qty DP <> Qty BOM
11 | 2200 | 1 | 44 | Qty MR <> Qty DP | Qty MR <> Qty DP
12 | 1 | 1 | 0 | Qty MR <> Qty BOM | Qty MR <> Qty BOM
13 | 114 | 2 | 0 | EXW > ETD | EXW > ETD
14 | 6 | 2 | 0 | ETD > ETA | EXW > ETD
15 | 124 | 2 | 3 | ETA > DOS Baseline Start and DOS Act/For Start | ETA > DOS Baseline START and DOS Act/For START
16 | 18 | 2 | 0 | DOS Baseline Start > DOS Baseline Finish | DOS Baseline START > DOS Baseline FINISH
17 | 34 | 2 | 0 | DOS Act/For Start > DOS Act/For Finish | DOS Act/For START > DOS Act/For FINISH
18 | 167 | 2 | 2 | Man.Start Contract Date > Man.FAT Contract Date | Man.Start Contract Date > Man.FAT Contract Date
19 | 96 | 2 | 1 | Man.Start Forecast/Actual > Man.FAT Forecast/Actual | Man.Start Forecast/Actual > Man.FAT Forecast/Actual
20 | 107 | 2 | 1 | Man.Start Contract Date > Man.Final/Pre-ship Insp. Cont. Date | Man.Start Contract Date > Man.Final/Pre-ship Insp. Cont. Date
21 | 105 | 2 | 1 | Man.Start Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual | Man.Start Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual
22 | 107 | 2 | 1 | Man.FAT Contract Date > Man.Final/Pre-ship Insp. Cont. Date | Man.FAT Contract Date > Man.Final/Pre-ship Insp. Cont. Date
23 | 127 | 2 | 1 | Man.FAT Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual | Man.FAT Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual
24 | 3549 | 2 | 73 | EXW <> Man.Final/Pre-ship Insp. Forecast/Actual | EXW <> Man.Final/Pre-ship Insp. Forecast/Actual
25 | 1824 | 3 | 25 | Manufacturing Status | Man.Final/Pre-ship Insp. Forecast/Actual < Today e flg “Working Status” non impostato.
26 | 2219 | 3 | 19 | Delivered Status | DOS Act/For FINISH < Today e flg “Delivered” non impostato
27 | 860 | 3 | 12 | Date Missing In MR
28 | 10299 | 3 | 82 | Date Missing In DP
T_ID | RNO | C_ID | ProgressPercentage | TileName | Conditions | Updated | Calculated
1 |  |  |  | Delayed DOS Start | DOS forecast STAR - DOS baseline START >0
2 |  |  |  | Delayed DOS Finish | DOS forecast FINISH - DOS baseline FINISH >0
3 |  |  |  | Delayed Departure Port | ATD – ETD >0
4 |  |  |  | Delayed Arrival Port | ATD – ETA >0 | XX-MR-00001
5 |  |  |  | Delayed Contract Date | Man. FAT Contract Date - Man. Start Contract Date>0. | XY-DP-00001
6 |  |  |  | Delayed Forecast/Actual | Man. FAT Forecast/Actual - Man. Forecast/Actual >0
7 | 5 |  |  | Delayed Final/Pre Ship | Man. Final/Pre ship. Inst Forecast/Actual - Man. Final/Pre ship. Insp. Contract Date >0
8 |  |  |  | Qty MR <> Qty DP | Qty MR <> Qty DP
9 |  |  |  | Qty MR <> Qty BOM | Qty MR <> Qty BOM
10 |  |  |  | Qty DP <> Qty BOM | Qty DP <> Qty BOM
11 |  |  |  | Qty MR <> Qty DP | Qty MR <> Qty DP
12 |  |  |  | Qty MR <> Qty BOM | Qty MR <> Qty BOM
13 | 5 |  |  | EXW > ETD | EXW > ETD
14 |  |  |  | ETD > ETA | EXW > ETD
15 |  |  |  | ETA > DOS Baseline Start and DOS Act/For Start | ETA > DOS Baseline START and DOS Act/For START
16 |  |  |  | DOS Baseline Start > DOS Baseline Finish | DOS Baseline START > DOS Baseline FINISH
17 |  |  |  | DOS Act/For Start > DOS Act/For Finish | DOS Act/For START > DOS Act/For FINISH
18 |  |  |  | Man.Start Contract Date > Man.FAT Contract Date | Man.Start Contract Date > Man.FAT Contract Date
19 | 4 |  |  | Man.Start Forecast/Actual > Man.FAT Forecast/Actual | Man.Start Forecast/Actual > Man.FAT Forecast/Actual
20 |  |  |  | Man.Start Contract Date > Man.Final/Pre-ship Insp. Cont. Date | Man.Start Contract Date > Man.Final/Pre-ship Insp. Cont. Date
21 |  |  |  | Man.Start Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual | Man.Start Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual
22 |  |  |  | Man.FAT Contract Date > Man.Final/Pre-ship Insp. Cont. Date | Man.FAT Contract Date > Man.Final/Pre-ship Insp. Cont. Date
23 |  |  |  | Man.FAT Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual | Man.FAT Forecast/Actual > Man.Final/Pre-ship Insp. Forecast/Actual
24 |  |  |  | EXW <> Man.Final/Pre-ship Insp. Forecast/Actual | EXW <> Man.Final/Pre-ship Insp. Forecast/Actual
25 |  |  |  | Manufacturing Status | Man.Final/Pre-ship Insp. Forecast/Actual < Today e flg “Working Status” non impostato.
26 |  |  |  | Delivered Status | DOS Act/For FINISH < Today e flg “Delivered” non impostato
27 |  |  |  | Date Missing In MR
28 | 2 |  |  | Date Missing In DP