## Issues
S. no | Issue Description | Design/Functional | Comment | Status
1 | In the user tab when the Supplier TT permission is given the popup shows undefined | Design | SS 1 | Open
2 | When the user is logged in and tries to access the Supplier Timetracking module > it shows Vendor Time tracking | Design | In POX it shows - Supplier ( SS 2 ) | Solved
3 | The header of the TT shows Vendor Time Tracking | Design | SS 3 | Open
4 | The icons for export to excel and customize cloumn not visible | Design | SS 4 | Open
5 | When we click on the plus icon to open a tt popup the plus icon is visible | Design | SS5 | Open
6 | The cancel Button icon is not visible as well | Design | SS 6 | Open
7 | When clicking on the TT some icons design is disturbed | Design | SS 7 | Open
8 | When we click on Save nothing happens > no informative message appears | Functional |  | Open
9 | When we click on cancel button the TT page becomes blank an have to refersh the page | Functional | SS 8 | Open
10 | When we click on release nothing happens have to refresh the page to look into the changes | Functional |  | Open
11 | Not able to Delete the Timesheet | Functional | SS 9 | Open
12 | The Project Manager currently being Defined by the field -( Project Manager) but in POX the project manager is defiened in the field - (IT Project Manager ) | Functional | Need to Discuss | Open
13 | Able to create and releasse the TT with a Project Manager who do not have any Role defeined for Supplier TT Permission | Functional | SS10 & SS11 | Open
14 | TT has Project manager defiened over it but when we login with the Project manager the Current Tab is visible to the PM and not able to view the TT which is released for his approval | Functional | SS12 & SS13 | Solved
15 | If delete the project for which the TT has been created and release the TT on opening becomes blank | Functional | SS 14 | Same in POX
16 | Will a email be send to the PM when the TT is released for approval | Functional | Need to Discuss | Open
17 | In Roles > custom Tab the design of the highlighted fields is disturbed | Design | SS15 | Open
18 | Showning the name Process instead of Project | Design | SS16 | Open
19 | The 2 Columns are Duplicated | Functional | SS17 | not an issue
20 | Last Submission Date Not showing | Functional |  | Open
21 | Actuals not coming in the project when TT is approved | Functional |  | Open
22 | When the TT is approved some column are coming blank | Functional |  | Open
23 | The comment popup is coming blank | Functional |  | Open
24 | When only Supplier TT permision is given > the user id also able to see and access the satndard TT aplication | Functional |  | Open
25 | Able to release the TT without any actuals | Functional |  | need to check
26 | The column shows IT Project Manager instead of Project Manager | Functional |  | Open
27 | Not able to adjust the size of columns | Functional |  | Open

## Sheet1
S.no | Module | Issue Description | Type | Status
1 | VTT | Timesheet created for the projects on which donothave PM defoiened over them | Functional | Closed
2 | VTT | Nothing happens when we click on Edit Button | Functional | Closed
3 | VTT | After the mesage'please enter actuals ' user is not able to release the timesheet | Functional | Closed
4 | VTT | Able to edit the actuals even after TT has been released | Functional | Closed
5 | VTT | Commetns are duplicated when TT is released | Functional | Closed
6 | VTT | The count on the register for Pending Approved is showing blank ( for PM ) | Functional | Closed
7 | VTT | The comment popup shows date and time both > it should show date only | Functional | Closed
8 | VTT | Actuals are not updating on Forecast | Functional | Open
10 | VTT | delete button is not working | Functional | Closed
S.no | Module | Issue Description | Type | Status
1 | VTT | Commetns are duplicated when TT is released | Functional | Closed
2 | VTT | The count on the register for Pending Approved is showing blank ( for PM ) | Functional | Closed
3 | VTT | The comment popup shows date and time both > it should show date only | Functional | Closed
4 | VTT | Actuals not updating on project when TT is released | Functional | Closed
5 | VTT | delete button is not working | Functional | Closed
6 | VTT | When we click on Cancel in pending or Approved tab it redirects us to Current tab > it should remain in the tab opened | Functional | Open

## Screenshot
0
SS 1
SS 2
SS 3
SS4
SS5
SS 6
SS 8
SS 9
SS10
SS11
SS12
SS13
SS14
SS15
SS16
SS17