## Q4-2023
Feature | Ticket | Activities | Sub-Activity | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25
Development
|  |  | Configure the Extension Hook on Pre-Prod | 2024-01-30: Sumit; 2024-02-25: Q4-2023 Production Release
POX-11619 |  | Hierarchical Map | Hierarchical Map - In Strategy Module | 2024-01-30: Sumit
POX-11407 |  | Cost Replacement | Bug fixing - PreProd, DEV | 2024-01-31: Sumit
| 2533 |  | Support ticket - Discussion with Luca | 2024-01-31: Sumit
POX-11409 |  | Template Management | Fill details of selected Template at time of new project creation | 2024-01-31: Sumit
|  |  | Saving of details is in-progress | 2024-02-01: Sumit
| 2694 |  | Reported issue on sella "project save" | 2024-02-01: Sumit
| 2694 |  | a Script check with Luca | 2024-02-05: Sumit
|  |  | resolved reported point by Luca on db-script | 2024-02-07: Sumit
| 2692 |  | Ferablobe Actual issue (Execution state) project | 2024-02-01: Sumit
| 2700 |  | Email to be send for Feraglobe | 2024-02-02: Sumit
|  |  | Redirection to the template management form create new Task popup | 2024-02-02: Sumit
POX-11409 |  | Template Management | Async process for template management | 2024-02-05: Sumit
| 2706 |  | Analyse the workflow status column on register(service request) | 2024-02-05: Sumit
| 2718 |  | Check mandetory field from Register- Reported by Federica | 2024-02-07: Sumit
POX-11519 |  | COS | Production update for the COS points | 2024-02-07: Sumit
| 2533 |  | Translink - reported Jira points by luca - Email to be send for MOM after discussion | 2024-02-08: Sumit
| 2734 |  | Need to remove unwanted association of field | 2024-02-09: Sumit
| 2533 |  | Jira points to be update for Prod | 2024-02-12: Sumit
| 2727 |  | Jira discussed point to be complete | 2024-02-12: Sumit
|  |  | Reported bug by QA cycle on templete management | 2024-02-12: Sumit
|  |  | Save As Template popup window changes | 2024-02-13: Sumit
|  |  | Bug fixing on Template management for reported points by QA | 2024-02-14: Sumit
| 2753 |  | Sella reported support ticket - Gantt | 2024-02-14: Sumit
|  |  | Save As Template and Quick new project Changes | 2024-02-16: Sumit; 2024-02-19: On-Leave; 2024-02-20: On-Leave
| 2777 |  | Sevice request to make the one wf for each collabration object - Robart | 2024-02-21: Sumit
| 2776 |  | Change the project wf - Service request - Robart | 2024-02-21: Sumit
| 2783 |  | Change User role and visibility issue on objects | 2024-02-21: Sumit; 2024-02-22: Sumit
| 2697 & 2781 |  | change the state of project in execution | 2024-02-21: Sumit
|  |  | Export to pdf in Portfolio | 2024-02-22: Sumit
|  |  | Cost Assignemnt issue on top down | 2024-02-22: Sumit
| 2533 |  | Jira point | 2024-02-22: Sumit
|  |  | Gantt - rolling tasks start date and finish date on parent task | 2024-02-23: Sumit
|  | SSO | KT by Rahul | 2024-01-30: Aman; 2024-02-25: Q4-2023 Production Release
|  |  | Document on SSO | 2024-01-31: Aman
POX-11409 |  | Template Management | Initiative image Lib Development | 2024-01-30: Aman
|  |  | Collabration - User controls saving | 2024-01-31: Aman; 2024-02-01: On Leave
POX-11404 |  | Collaboration - Possibility to link the «Identification» section in WF | Reported Bug fixing | 2024-02-02: Aman
POX-11409 |  | Template Management | Attachment of objects for new template management | 2024-02-05: Aman
|  |  | Bug fixing for the collabration Item for Template Management(user controls | 2024-02-05: Aman
|  |  | Bug fixing and summarization on reported points on TM | 2024-02-06: Aman
|  |  | Reported query on SSO raised by Federica | 2024-02-06: Aman
|  |  | show image from choose template at time of project creation | 2024-02-06: Aman
|  |  | Dublicate object code of collabration | 2024-02-06: Aman
|  |  | Asyc process reported points in Project copy.vb file | 2024-02-09: Aman
|  |  | Reported Bug fixing on Template management | 2024-02-09: Aman
POX-11649 |  | SSO Improvement | SSO Improvement - Analysis for all the existing algorithm- Document Creation | 2024-02-12: Aman
|  |  | Analysis on Encrpt/Decrpt algorithm and Document create | 2024-02-16: Aman
|  |  | SSO implementation on Dev | 2024-02-16: Aman; 2024-02-19: Aman
|  | Template Management | Reported Bug fixing | 2024-02-16: Aman
| 2759 |  | Issue on collaboration register | 2024-02-16: Aman
|  |  | Make env. For SSO for QA verification | 2024-02-19: Aman; 2024-02-21: Aman
|  |  | Bug fixing on Template Management reported by QA verification | 2024-02-19: Aman
|  |  | Detail out for the reason for Not saved template in notification popup | 2024-02-20: Aman
|  |  | Performance on template | 2024-02-22: Aman
|  |  | Bug fixing for reported point by QA | 2024-02-23: Aman
POX-11409 |  | Template Management | Pre condition to create a template | 2024-01-30: Ayush; 2024-02-25: Q4-2023 Production Release
|  |  | Create collabration items with First step | 2024-01-31: Ayush
|  |  | Attachment copy for new Initiative for template | 2024-01-31: Ayush
|  | SSO | KT by Rahul | 2024-01-30: Ayush
|  |  | Template register page developments - a) Comment section read only b) Status read only c) WSJF read only d) Template at forst step of WF in template register | 2024-02-01: Ayush
POX-11409 |  | Template Management | Save As permission for template | 2024-02-01: Ayush
|  |  | Reported Bug on Inititive Save on DEV | 2024-02-01: Ayush
|  |  | Management State for the Template Register | 2024-02-02: Ayush
|  |  | Delete template functionality from template register | 2024-02-02: Ayush
|  |  | redirection from Initative WS to Template register | 2024-02-02: Ayush
|  |  | Bug fixing for the template register and details page | 2024-02-05: Ayush
|  |  | Added Template Log for Template to Project | 2024-02-08: Ayush
|  |  | Asyc process reported points in Project copy.vb file | 2024-02-09: Ayush
|  |  | Reported Bug by QA cycle on Template management | 2024-02-09: Ayush
POX-11603 |  |  | Graphical change to the Risk Matrix - Analysis | 2024-02-12: 1/2 leave; 2024-02-13: Ayush; 2024-02-14: Ayush; 2024-02-15: Ayush
|  |  | reported Bug on completed development by QA cycle | 2024-02-12: Ayush; 2024-02-13: Ayush; 2024-02-14: Ayush; 2024-02-15: Ayush
|  |  | Changes for the Quick New Project | 2024-02-13: Ayush
|  |  | Changes on Template register | 2024-02-16: Ayush; 2024-02-19: On_leave; 2024-02-20: On_leave
|  |  | Bug fixing on the reported issue | 2024-02-21: Ayush; 2024-02-22: Ayush
POX-11409 |  | Template Management | Initiative image Lib Development | 2024-01-30: NandLal; 2024-02-25: Q4-2023 Production Release
|  | Strategy | Value Stream Design Point | 2024-01-31: NandLal
|  |  | Co-Authot Popup Design point | 2024-01-31: NandLal
|  |  | Co-Author chat boat design enhancement | 2024-02-01: NandLal
|  |  | Update pre-prod for the bug fixes | 2024-02-01: NandLal
| 2638 |  | Reported COS popup design | 2024-02-01: NandLal
POX-11409 |  | Template Management | Design issue on template management | 2024-02-01: NandLal
|  |  | Handle the widget size for change request Collabration | 2024-02-01: NandLal
|  |  | Adding Tooltip in the COS popup in full application | 2024-02-02: NandLal
|  |  | COS design for Template Creation | 2024-02-02: NandLal
POX-11409 |  | Template Management | Save as template design issue | 2024-02-05: NandLal
|  |  | import from library design issue | 2024-02-05: NandLal
|  |  | Bug fixing on design issues on Template Management | 2024-02-06: NandLal
|  |  | Project status widget height issue reported bug by QA | 2024-02-08: NandLal
|  |  | Mackup for CO-Author Design | 2024-02-08: NandLal
|  |  | change layout for CO-Author Design - Changes | 2024-02-09: NandLal
|  |  | Design bug fixing on reported QA points | 2024-02-09: NandLal
|  |  | Mauckup New created project on project register Heighlight | 2024-02-09: NandLal; 2024-02-12: On-leave; 2024-02-13: Nandlal
|  |  | Design change for the "Save As Template" and "Quick New Project" | 2024-02-13: Nandlal
|  |  | Bug fixing on design issues on Template Management | 2024-02-19: Nandlal
|  |  | Reported points by Amrit on previous development | 2024-02-19: Nandlal
|  |  | Bug fixing on reported bug | 2024-02-21: Nandlal
|  |  | Design issue on OKR widget | 2024-02-22: Nandlal
POX-11411 |  | Co-Auther | Training file Creation with codions (generic) | 2024-01-30: Rajesh; 2024-02-01: On Leave; 2024-02-25: Q4-2023 Production Release
|  |  | Restrict the user to associate the project on strategy if strategy is not in open state from co-author chat window on drag & drop. | 2024-02-02: Rajesh
|  |  | fine tune the model | 2024-02-06: Rajesh
|  |  | Convert JSON file to JSON L | 2024-02-06: Rajesh
| 2694 |  | issue on detail page (crash issue internal) | 2024-02-07: Rajesh
|  |  | New Model cycle & fine tune | 2024-02-08: Rajesh
|  |  | To be Analyze the collabration custom fields to be implement on Kanban | 2024-02-08: Rajesh
|  |  | RnD on azure Open AI Analysis | 2024-02-09: Rajesh; 2024-02-12: Rajesh; 2024-02-19: Rajesh
|  |  | New Approch for linking with Azure Open AI | 2024-02-19: Rajesh
|  |  | A technical document related to the AI activities and linking with SPM | 2024-02-19: Rajesh
|  |  | to be create a Polly for selecting the CO-Author name | 2024-02-13: Rajesh
|  |  | optimization of Template Management Saving | 2024-02-20: Rajesh
|  |  | Bug fixing on Inititive workspace | 2024-02-21: Rajesh; 2024-02-22: Rajesh
|  |  | Attachment not visible on the template collabration item | 2024-02-23: Rajesh
POX-11519 |  | COS | COS characters increase - Changes in Database Side | 2024-01-31: Ravi D; 2024-02-25: Q4-2023 Production Release
|  |  | Bug fixing on COS Character increase Point | 2024-02-02: Ravi D
|  |  | Pre-Prod to be update for the done points | 2024-02-05: Ravi D
POX-11539 |  | Geo coordinates | Bug fixing on reported feature | 2024-01-31: Ravi D
|  |  | Bug fixing on reported feature | 2024-02-02: Ravi D
POX-11409 |  | Template Management | Document Analysis | 2024-01-31: Ravi D
| 2697 |  | create a db-script for provide a list of project on the last step | 2024-02-05: Ravi D
|  |  | Summarized cycle on template management | 2024-02-06: Ravi D
|  |  | To be update the spmq4 link for acceptance | 2024-02-08: Ravi D
|  |  | Added Template Log on Save as Template | 2024-02-08: Ravi D
|  |  | Bug fixing on reported QA points | 2024-02-09: Ravi D
|  |  | Analysis for the Login Algorithms for SHA-1 to SHA-256 | 2024-02-09: Ravi D
| 2740 |  | Strategy theam Name update on Project register | 2024-02-12: Ravi D
POX-11409 |  | Template Management | Discussion for new changes on Template management with internal team | 2024-02-12: Ravi D
POX-11617 |  |  | Discussion before implementation/Development start | 2024-02-13: Ravi D
POX-11603 |  |  | Graphical change to the Risk Matrix - Analysis | 2024-02-13: Ravi D
POX-11617 |  | separate login links in the email | Added int the email notification | 2024-02-14: Ravi D; 2024-02-15: Ravi D; 2024-02-16: On-Leave
|  |  | Bug fixing on Template Management reported by QA verification | 2024-02-19: Ravi D
|  |  | Script for old data related to the Email-Notification | 2024-02-19: Ravi D
|  |  | Reported points by Amrit on previous development - functional points | 2024-02-19: Ravi D
|  |  | optimization of Template Management Saving | 2024-02-20: Ravi D; 2024-02-21: On-Leave
|  |  | overall Cycle on all the development point | 2024-02-22: Ravi D
|  |  | Pre-inital for Update the prod process. | 2024-02-22: Ravi D
|  |  | Changes for feature Pox-11617 | 2024-02-22: Ravi D
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On-hold

## Q1-2024
Feature | Ticket | Activities | Sub-Activity | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31
Development
On-Leave
|  | Save Baseline | Gap document on "Save Baseline" with Pox-Axa | 2024-02-27: Sumit
|  |  | Create tab on workflow configuration and apply conditional object creation | 2024-02-28: Sumit
| 2803 |  | Initiative register dublicate filter value | 2024-02-28: Sumit
|  |  | Jira Dublicate Task Issue | 2024-02-29: Sumit
| 2786 |  | Sella Workflow issue- info icon | 2024-03-04: Sumit
| 2810 |  | Issues on relations and dependency | 2024-03-05: Sumit
|  |  | Feraglobe Admin permission to be restore -(internal) | 2024-03-06: Sumit
|  |  | Process for saving the project and check conditions in db-side | 2024-03-06: Sumit
| 2798 |  | to be create a db-script for previous assignments | 2024-03-07: Sumit
| 2832 |  | Gantt Duration in Sec | 2024-03-08: Sumit
| 2853 |  | Jira issue | 2024-03-12: Sumit
|  |  | Adding DFS reference in Object creation | 2024-03-13: Sumit; 2024-03-15: onHold
| 2856 |  | Sella - service request for gantt date change | 2024-03-13: Sumit; 2024-03-20: Sumit
| 2864 |  | list of projects and task for high duration | 2024-03-14: Sumit
| 2888 |  | dublicate code resolve | 2024-03-20: Sumit
| 2885 |  | Jira reported issue | 2024-03-21: Sumit
| 2893 |  | Bpm Object not visible at user end | 2024-03-21: Sumit
|  |  | Status report for the Document Management | 2024-03-21: Sumit
|  |  | Internal bug fixes | 2024-03-22: Sumit
|  |  | Checking the group by option for Cost Element in Cost details widget | 2024-03-27: Sumit
|  |  | Internal bug fixes & Support | 2024-03-28: Sumit
|  |  | Final Cycle for UAT -1 reported points | 2024-03-29: Sumit
|  |  | Sella cost top down approach reported Bug | 2024-02-26: Aman
|  | Financial Widgets | Analysis and Gap document on "Financial Widget" | 2024-02-27: Aman
|  |  | Finencial widget - Group By | 2024-02-28: Aman; 2024-02-29: ON-HOLD
|  | Docment Management | Document Type in Standard code - New page | 2024-02-27: Aman
|  |  | Column label change in Company setting and impact on widget | 2024-03-01: Aman
|  |  | Make Expendeture and Accural column editable in Cost widget | 2024-03-04: Aman
|  |  | procedure to create bpmobject for DM | 2024-03-06: Aman
|  |  | Handle impacts on the other areas in Intiative Workspace for Lable change | 2024-03-07: Aman
|  |  | Lock project workspace when import data in in progress | 2024-03-08: Aman
|  |  | Bug fixing on the released points on the dev by Internal QA | 2024-03-11: Aman
|  |  | Active/Inactive drop down and datatable for BPM controls on objects | 2024-03-13: Aman; 2024-03-14: Not Available
|  |  | handling of custom field for top down for cost | 2024-03-18: Aman
|  |  | Document Kpi for Status report | 2024-03-20: Aman; 2024-03-21: On Leave
|  |  | Internal Bug fixing | 2024-03-22: Aman
|  |  | Create tab in cost custom fields for top down field selection | 2024-03-27: Aman
|  |  | Reported Bugs by Armando Sir | 2024-03-27: Aman
|  |  | Internal Bug fixing | 2024-03-28: Aman
|  |  | Final Cycle for UAT -1 reported points | 2024-03-29: Aman
|  | Tasks Properties (chargeble, type) | Tasks Properties (chargeble, type) | 2024-02-26: Ayush
|  |  | Creation of the Angular Api for Comments | 2024-02-29: Ayush
|  |  | Changes for Company setting for adding one new entry for "Document status" threashold | 2024-03-01: Ayush
|  |  | Change in the Status report for "Document Status" | 2024-03-01: Ayush
|  |  | Adding a new flag for Action Popup for Form configuration | 2024-03-04: Ayush
|  |  | Extension hook to be working process - write service for testing | 2024-03-04: Ayush
|  |  | New user control for fixed controls for document management | 2024-03-06: Ayush
|  |  | reported Bug by QA on Manage Chargeable actitivity | 2024-03-07: Ayush
|  |  | Static fields for the Document checklist process | 2024-03-11: Ayush
|  |  | Status report for the document Api | 2024-03-11: Ayush; 2024-03-14: Not Available
|  |  | Business API issue changes | 2024-03-12: Ayush
|  |  | handling of checklist permission based on selection of process | 2024-03-13: Ayush
|  |  | sort of list in the list box | 2024-03-13: Ayush
|  |  | Bug fixing reported by Internal QA | 2024-03-18: Ayush; 2024-03-21: On Leave
|  |  | Reported Bugs by Armando Sir | 2024-03-27: Ayush
|  |  | Document management - enable mendatory and weight field on creation | 2024-03-28: Ayush
|  |  | Final Cycle for UAT -1 reported points | 2024-03-29: Ayush
| 2799 |  | User login loading issue reported by Sella | 2024-02-26: Rajesh
|  |  | Project Size UC | 2024-02-26: Rajesh; 2024-02-27: Rajesh
|  |  | Comment widget - New Genric widget for Workspace | 2024-02-27: Rajesh; 2024-03-05: Rajesh
|  |  | Finencial widget - Comment widget | 2024-02-28: Rajesh
|  |  | SPM Initiative Workspace Angular Widget Management | 2024-02-29: Rajesh; 2024-03-04: On-leave; 2024-03-05: Rajesh
|  |  | Confirmation message for angular widget operation | 2024-03-08: Rajesh
|  |  | Date formate and RO for widget | 2024-03-08: Rajesh
|  |  | Business API issue changes | 2024-03-12: Rajesh
|  |  | Bug fixes issue | 2024-03-12: Rajesh
|  |  | seprate the application for Customer specific | 2024-03-13: Rajesh; 2024-03-15: On-Hold
|  |  | Changes in custom fields to move the label from setting to custom fields | 2024-03-14: Rajesh
|  |  | Adding validation for a number field for custom fields | 2024-03-19: Rajesh
|  |  | Hide and rename on the details page | 2024-03-20: Rajesh
|  |  | Interanl Bug fixing | 2024-03-22: Rajesh; 2024-03-27: On Leave
|  |  | Adding Property in the company setting for Exp vs Acc | 2024-03-28: Rajesh
|  |  | Design issue Verifiation -> after merging the new branch on develop | 2024-02-26: NandLal
|  |  | Vendor Time Tracking - Angular Pages and component Analysis and build | 2024-02-27: NandLal
|  |  | Vendor Time Tracking -"Register" page | 2024-02-28: NandLal; 2024-03-01: ON-HOLD
|  |  | Edit VTT timesheet | 2024-02-29: NandLal
|  |  | Design change for "Status Threshold Settings" | 2024-03-01: NandLal
|  |  | Implement the required chaanges for "Angular Genric Widget" | 2024-03-01: NandLal; 2024-03-05: NandLal
|  |  | Company Setting Label -Changes | 2024-03-04: NandLal
|  |  | Form builder css changes | 2024-03-04: NandLal
|  |  | Activity details widget custom column design issue | 2024-03-05: NandLal
|  |  | relationship and dependency boc field design issue | 2024-03-05: NandLal
|  |  | Design correction for the form builder | 2024-03-06: NandLal
|  |  | Document Management Design Issue on the conditional flow and object creation | 2024-03-07: NandLal
|  |  | Confirmation message for angular widget operation | 2024-03-08: NandLal
|  |  | Internal Bug fixing | 2024-03-12: NandLal
|  |  | Change in the label to add new columns | 2024-03-14: NandLal
|  |  | Auto Update creation popup design change | 2024-03-15: NandLal
|  |  | Custom fields for cost and creation of multiple tabs | 2024-03-15: NandLal
|  |  | Bug fixing by Internal QA | 2024-03-19: NandLal
|  |  | Inport Design issue to be fix | 2024-03-21: NandLal
|  |  | Create tab in cost custom fields for top down field selection | 2024-03-27: NandLal
|  |  | Design points by QA | 2024-03-28: NandLal
|  |  | Discussed and analysis on reported point by Sella on Resouce assignment cost assign | 2024-02-26: Ravi D
|  |  | Analysis on the current developments -> Document Management Process | 2024-02-26: Ravi D
|  | Repo Management | Align the Master branch with other SPM branches | 2024-02-26: Ravi D
| 2798 | Sella support ticket | Create db-script for resolved the service request raised by sella for resouce rate | 2024-02-27: Ravi D
|  |  | Table schema for "Custom widget", "Auto Object creation" | 2024-02-28: Ravi D
|  |  | Development plan to be create for the first phase for AXA migration | 2024-02-29: Ravi D
|  |  | Gap between the Document managemnet for required Bpm controls and functionaling | 2024-03-01: Ravi D
|  |  | Analysis on finincil widgets | 2024-03-01: Ravi D
|  |  | Start Development analysis on IC loader for Extension hook | 2024-03-04: Ravi D; 2024-03-05: Ravi D
| 2798 | Sella support ticket | to be create a db-script for previous assignments | 2024-03-05: Ravi D
|  |  | Run the appropriate cycle for quality of the features | 2024-03-08: Ravi D
|  |  | Project Data import changes | 2024-03-11: Ravi D
|  |  | Status report alalysis and design | 2024-03-12: Ravi D; 2024-03-14: Not Available
|  |  | Customer specific development for the Angular and Api | 2024-03-13: Ravi D; 2024-03-14: Not Available
|  |  | Run cycle for development demo process | 2024-03-13: Ravi D
|  |  | Analysing for the Top down planning for the cost based on the selected field | 2024-03-18: Ravi D
| 2878 |  | Service Request from rotbert walters for remove the job title - Master | 2024-03-18: Ravi D
|  |  | Bug fixing on QA reproted issues by internal team | 2024-03-18: Ravi D
|  |  | Import IC loader configuration with provided api service | 2024-03-20: On Leave; 2024-03-21: Ravi D
|  |  | Reported Bugs by Armando Sir | 2024-03-27: Ravi D
|  |  | UAT-2 tickets Analysis | 2024-03-28: Ravi D
|  |  | Internal Bug fixing | 2024-03-28: Ravi D
|  |  | Final Cycle for UAT -1 reported points | 2024-03-29: Ravi D
|  |  | Seprate branch for Axa_Beta link | 2024-03-31: Ravi D

## Q1-2024_1
Feature | Ticket | Activities | Sub-Activity | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03
Development
| 2856 |  | Project duration (gantt - 5 years) | 2024-04-01: Sumit; 2024-04-13: Working on VTT; 2024-04-20: VTT Bug fixing; 2024-04-27: COS view in RE
| 2928 |  | project restore from back to main db | 2024-04-02: Sumit
|  |  | cost assignment on Milestone | 2024-04-04: Sumit
| 2906 |  | Import Excel for standard functionality | 2024-04-04: Sumit
| 2856 |  | Project duration (gantt - 5 years) | 2024-04-04: Sumit
| 2942 |  | BT- Code dublicate | 2024-04-05: Sumit
| 2941 |  | Baseline owner name | 2024-04-05: Sumit
|  |  | VTT Edit functionality on angular side for view | 2024-04-05: Sumit; 2024-04-08: Sumit; 2024-04-11: On Leave
| 2952 |  | Code deblicate on BT - Anubrij | 2024-04-09: Sumit
|  |  | VTT Completion | 2024-04-11: Sumit
|  |  | VTT reported bugs | 2024-04-18: Sumit
| 2965 |  | Translink Project creation Date issue | 2024-04-18: Sumit
|  |  | RE COS Widget | 2024-04-22: Sumit
|  |  | VTT reported bugs | 2024-04-24: Sumit; 2024-04-25: Sumit; 2024-04-26: Sumit
|  |  | COS view in RE | 2024-04-30: Half Day leave
|  |  | Internal Bug fixing points | 2024-04-29: Sumit; 2024-04-30: Sumit
|  |  | VTT - Angurar Register Page | 2024-04-01: Aman; 2024-04-03: OnLeave; 2024-04-13: Not Available; 2024-04-20: RE Changes; 2024-04-27: RE Reported Bugs
|  |  | Home page create project issue on UAT-1 | 2024-04-01: Aman
|  |  | Register funcationality from VTT (To be complete today) | 2024-04-04: Aman
|  |  | RE development for the Resource view | 2024-04-08: Aman
|  |  | RE development for the Project view | 2024-04-09: Aman
|  |  | RE Calender funcationaltity working | 2024-04-10: Aman
|  |  | RE Resource assignment view - RR,Edit, Delete | 2024-04-12: Aman
|  |  | Resource Availability View | 2024-04-15: Aman
|  |  | RE Performance optimization | 2024-04-17: Aman
|  |  | RE Internal Bug | 2024-04-22: Aman
|  |  | COS View | 2024-04-25: Aman
|  |  | RE ported Points | 2024-04-29: Aman; 2024-04-30: Aman
|  |  | VTT - Angular WebApi customer Specific | 2024-04-01: Ayush; 2024-04-13: Working on VTT Api; 2024-04-20: RE Layout Development; 2024-04-27: Status Reported Bugs
|  |  | VTT - Angular WebApi Register services | 2024-04-03: Ayush
|  |  | VTT - Add/Edit/Delete api | 2024-04-04: Ayush
|  |  | User edit for resource lnking | 2024-04-03: Ayush
|  |  | Migration for RE | 2024-04-08: Ayush
|  |  | RE filter development | 2024-04-08: Ayush
| 2928 |  | Send email error | 2024-04-10: Ayush
|  |  | RE Tab Preference | 2024-04-09: Ayush
|  |  | VTT api Changes | 2024-04-11: Ayush
|  |  | Document register File visible column for bpm objects | 2024-04-11: Ayush
|  |  | DepOps integration on SPM DEV | 2024-04-12: Ayush
|  |  | Permission -Custom sepration in Role | 2024-04-11: Ayush
|  |  | RE tabs loading and maintain preferences | 2024-04-16: Ayush
|  |  | Bug fixing on exl points | 2024-04-19: Ayush
|  |  | RE Layout development | 2024-04-22: Ayush
|  |  | Status Report development | 2024-04-22: Ayush
|  |  | Status Report Bug fixing | 2024-04-29: Ayush
|  |  | Sepration of Cutomer Angular and Api solution | 2024-04-01: Rajesh; 2024-04-04: OnHold; 2024-04-13: Working on RW Activities; 2024-04-20: Activity Manager Role; 2024-04-27: Status Report Bug fixing
|  |  | VTT - Angular WebApi Edit page | 2024-04-03: Rajesh
|  |  | UAT-1 reported points | 2024-04-03: Rajesh
|  |  | VTT - ADD funcationality with linking with API | 2024-04-04: Rajesh
|  |  | Kanban development in SPM for collabration registers | 2024-04-05: Rajesh
|  |  | RE Group By funcationality | 2024-04-09: Rajesh
|  |  | RE Department filter and DM role loging on RE | 2024-04-09: Rajesh
|  |  | Inititive wf close status job from pox to spm feature | 2024-04-11: Rajesh
|  |  | Export to excel on Pivot in RE | 2024-04-12: Rajesh
|  |  | Rename labels for Project detail section | 2024-04-16: Rajesh
|  |  | Status Report - Gap to be implement | 2024-04-17: Rajesh
|  |  | New Role implementation | 2024-04-18: Rajesh
|  |  | Status Report development and bug fixing | 2024-04-23: Rajesh
|  |  | Internal Bug fixes points | 2024-04-29: Rajesh
|  |  | VTT design work on SPM related to VTT angular application | 2024-04-01: NandLal; 2024-04-02: On Leave; 2024-04-13: Working on Status Report; 2024-04-20: Re Design Points; 2024-04-27: Overall Design points
|  |  | Design Points on Previous release UAT-1 for Standard | 2024-04-03: NandLal
|  |  | Provide the limitations on new angular | 2024-04-04: NandLal
|  |  | RE points design developments | 2024-04-08: NandLal
|  |  | Status Report | 2024-04-10: NandLal
|  |  | VTT design points | 2024-04-11: NandLal
|  |  | Design changes for Role | 2024-04-12: NandLal
|  |  | Design changes for File in bpm object register | 2024-04-12: NandLal
|  |  | Desgin change in WF for New Job icon and popup | 2024-04-12: NandLal
|  |  | RW Design changes sugested by Anubrij | 2024-04-15: NandLal
|  |  | RE Design changes | 2024-04-16: NandLal
|  |  | VTT reported points related to design | 2024-04-17: NandLal
| 2966 |  | BOC design issue | 2024-04-17: NandLal
|  |  | RE development design points | 2024-04-23: NandLal
|  |  | Internal Bug fixes points | 2024-04-29: NandLal
|  |  | Analysis on the UAT-2 points for VTT | 2024-04-01: Ravi D; 2024-04-13: Working on Import Actual; 2024-04-20: RE COS Development; 2024-04-27: RE Bug fixing
|  |  | Analysis on the UAT-2 points for Status project feature | 2024-04-01: Ravi D
|  |  | Create analysis doc for the Gap for UAT-2 for AXA | 2024-04-01: Ravi D
|  |  | create a seprate Repo for AXACustomSPM for adding different solutions | 2024-04-01: Ravi D
|  |  | VTT - Angular WebApi Edit page Service Api side | 2024-04-03: Ravi D
|  |  | UAT- 1 Points | 2024-04-05: Ravi D
|  |  | RE start analysis for development points | 2024-04-05: Ravi D
|  |  | RE Filter development | 2024-04-08: Ravi D
|  |  | VTT hosting on link for dev for testing purpose | 2024-04-09: Ravi D
|  |  | Customize procedure for Workflow Closure Status - ticket 505 | 2024-04-10: Ravi D
|  |  | Document for the custom development in SPM Standard | 2024-04-11: Ravi D
|  |  | VTT run for unit testing and relesed for QA | 2024-04-11: Ravi D
|  |  | Board revise for UAT-2 features | 2024-04-11: Ravi D
| 2955 |  | Sella TT issue to be verify and resolve | 2024-04-11: Ravi D
|  |  | Start the import Actual funcationality | 2024-04-12: Ravi D
|  |  | RE Changes for Replace resources | 2024-04-15: Ravi D
|  |  | RE performace change | 2024-04-17: Ravi D
|  |  | Status report Gap analysis | 2024-04-17: Ravi D
|  |  | Import actual reported bugs | 2024-04-17: Ravi D
|  |  | Demo Calls on VTT and RE | 2024-04-19: Ravi D
|  |  | RE COS Development | 2024-04-22: Ravi D
|  |  | Overall Development points | 2024-04-23: Ravi D; 2024-04-29: Ravi D
|  |  | Prepare for the demo call | 2024-04-30: Ravi D
|  |  | Overall Development bug fixes points | 2024-04-30: Ravi D

## Q1-2024_2
Feature | Ticket | Sub-Activity | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-18 | 2024-05-19 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-25 | 2024-05-26 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31
Development
Access |  | Handling of Cost Columns based on Role configuration | 2024-05-06: Sumit
| 3008 | Resource Assignment on Milestone | 2024-05-06: Sumit
| 3014 | RW - baseline issue | 2024-05-07: Sumit
|  | Status report Points in document - Funcational point | 2024-05-08: Sumit
RE |  | Reported points From UAT-2 for COS View in RE | 2024-05-06: Aman
|  | TT Auto Save | 2024-05-06: Aman
|  | RE Filter points reported from UAT - 2 | 2024-05-07: Aman
|  | New filters on RE for resource | 2024-05-08: Aman
Status Update |  | Reported points from UAT-2 onStatus Report | 2024-05-06: Ayush
|  | RE Log on Develop | 2024-05-06: Ayush
|  | RE Filter points reported from UAT - 2 | 2024-05-07: Ayush
|  | UAT - 2 Points | 2024-05-08: Ayush
Activity manager |  | Implementation of Activity Manager in SPM | 2024-05-06: Rajesh
|  | Status Report - Email functionality to be check | 2024-05-07: Rajesh
|  | UAT- 2 points | 2024-05-08: Rajesh
STD |  | Overall Design Points on SPM for repoeted points and new dev | 2024-05-06: Nand Lal; 2024-05-07: On Leave
|  | Completion of design for the Visualization point | 2024-05-08: Nand Lal
|  | Design point on RE module | 2024-05-08: Nand Lal
|  | Analysis and Activity brackup for new development and sprint Planning | 2024-05-06: Ravi
|  | AXA Migration UAT-3 discussion call | 2024-05-07: Ravi
|  | TT changes for ON-Hold activity | 2024-05-08: Ravi
|  | Alignment meeting with Armando sir for UAT-3 | 2024-05-09: Ravi

## UAT-2 Activities
# | Points/Functionalities /Features |  | Status | Progress | Target Date | Comment
1 | Import actuals (costs) |  | Dev Done | 100% | 2024-04-15 | Information required from Armando sir side
Create a new Extension Hook for "Import Actual Expense"
Handling of new extion service in import register page
create a web Api for import data
Show log
2 | BPM Data Table Active/Inactive records functionality |  | Done | 100% |  | Done in UAT-1
3 | Status Update (costs label) |  | Open | 0%
show the register page for Status report
Show the edit page for the objects
adding functionality in portfolio to create a objects for selected projects
Change labels for the Cost Status in status reprot page
Setting permission
4 | Vendor Time Tracking |  | Dev Done | 100% | 2024-04-14 | Bug fixes in Progress (8 open points reproted by Mohit)
To be done tommarow 1/2 half
Sudha Reported few gap as well.
5 | New Resource Explorer Module |  | In-progress | 70% | 2024-04-20
|  | View by resources and projects | Dev Done
|  | View by project and resources | Dev Done
|  | Group by department, any RBS available, job title, skill, internal/external, etc | In-progress |  |  | it is now work as a COS View
|  | Possibility to set easily the period like Year to date, this year, last year, period from to (year and quarter), I suggest that the number of year visualized will be few 2-3 possibility to set how many years are visible. This is to improve the performance (I assume that if they need to view a large range of year they can use the dashboard) | Dev Done
|  | PTB available | Dev Done
|  | The department manager user can view only the resource belong his department | Dev Done
|  | A user that is like a team leader can view only the resource belong his RBS | Open
|  | Available filters to select programs, portfolios and scenarios | Dev Done
|  | Standard permission read-only /read-write | Dev Done
|  | Standard SPM registers functionalities (column ordering, column filtering, column ordering, group by, excel export, etc) | Dev Done
|  | Resource replacement | Dev Done
|  | RE Workspace Layout and widget labeling | In-progress
6 | Benefit Management AXA (Value Realization) |  | from UAT-1 | 0% |  | Information required from Armando sir side
7 | Cost assignment over milestone |  | Done | 100%
8 | Process change - EPIC and Project process |  | from UAT-1 | N/A |  | N/A
9 | Status report - Checklist data in Status report |  | Open | 80% | 2024-04-15
10 | Project Manager Role for AXA |  | In discussion | 0% |  | In discussion and analysis
11 | Activity Manger Role implementation |  | In-progress | 50%
12 | Customize procedure for Workflow Closure Status - ticket 505 |  | Done | 100%
13 | Add file column in Team Space and in the Document Tab - ticket 510 |  | Done | 100%
14 | Kanban Collabration register
15 | Gantt - Remove Timeline
16 | Renaming Initiative Manager to project Manager field

## To-Do ->
Milestone Assignment
SAAS adminstrator Application
| CC page |  |  | to be decide for the junior for create a new module
After UAT-2
| Resoure assignment on Milestone |  |  | Can go later
| implementation on Cost |  |  | Should be in UAT -2
refinement of the implementation
RE Filter
RE filter should be implemented for loading in Client side. (currently using the server side controls)
Comment widget should be in merge in the AXA custom Angular application currently it is in the SPMStandard Angular application
implementation on Workflow design for closed status Job association (done for AXA for now)
Handling the Capacity detail widget in the RE regarding for the Demand and Execution state of project
Brainstoming for the RE module
Status reprot Card changes for "Schedule" "Team" to show all Data. And other hanges
Project Detail section is very slow. Need to check the reason
RE state management and refereshing pages/Widgets
RE Workspace for creating widgets as Project workspace.
| dynamic COS binding for the layers for RE COS view currently it is based on AXA defined COS layers |  |  | done
Create from Project for Status Update permission to be check.
Points Raised by GG Sir |  |  |  | To be done as a hotfix
0 | Auto save in Timesheet
1 | Work Type on Non working Activities | Uppwise CWM | Chandan | Mid of May
2 | Project is ON-Hold | Uppwise CWM | Ravi Dangi
> Open the Project
>Edit Project
> Add Time Over timesheet
* assignment will be visible in the Timesheet * Can not create a new assignment from TT or Workspace * Can add the hours on the assinged assignment for the user
3 | Program Management |  | Chandan | May Last
3.1 | Project can be assigned to One module -> remove this limitation Can assign one project on multiple progam
3.2 | Add Program KPI's (value Realization) | Uppwise CWM | Aman
4 | Impact on Analytics to be plan
5 | Resoure assignment on Milestone
| Extension hook service for write report. (details required) |  |  | After UAT-3