## Sheet1
Id | Name | UAT? | Start | Finish | Duration | Baseline Start | Baseline Finish | Baseline Duration | Actual Start | Actual Finish | % Done | Predecessors | Successors | Total Cost | Total Benefit | Total Effort
1 | AXA Migration | Cost Assigned | 2024-01-18 | 2024-11-29 | 221 days |  |  | 0 day | 2024-01-18 |  | 25 |  |  |  | 0
2 | Phase 01 - Preparation |  | 2024-01-18 | 2024-02-13 | 19 days |  |  | 0 day | 2024-01-18 | 2024-02-13 | 100
3 | Migration Kick-Off |  | 2024-01-18 | 2024-01-18 | 1 day |  |  | 0 day | 2024-01-18 | 2024-01-18 | 100 |  | 4;6;10;11
4 | Configuration Backlog |  | 2024-01-19 | 2024-02-01 | 10 days |  |  | 0 day | 2024-01-19 | 2024-02-01 | 100 | 3 | 5
5 | Implementation Planning |  | 2024-02-02 | 2024-02-08 | 5 days |  |  | 0 day | 2024-02-02 | 2024-02-08 | 100 | 4 | 7
6 | As-Is Reverse engineering |  | 2024-01-19 | 2024-02-12 | 17 days |  |  | 0 day | 2024-01-19 | 2024-02-12 | 100 | 3 | 7
7 | Migration Planning Meeting |  | 2024-02-13 | 2024-02-13 | 1 day |  |  | 0 day | 2024-02-13 | 2024-02-13 | 100 | 5;6
8 | Phase 02 - Implementation of Functional GAPS |  | 2024-01-19 | 2024-05-29 | 91 days |  |  | 0 day | 2024-01-18 |  | 39
9 | Demand Process | UAT1 | 2024-01-19 | 2024-04-08 | 56 days |  |  | 0 day | 2024-01-18 |  | 85
10 | Standard Activities Template on Project Creation | UAT1 | 2024-01-19 | 2024-02-29 | 30 days |  |  | 0 day | 2024-01-19 | 2024-02-29 | 100 | 3 | 16;17;30
11 | Top-Down Cost Planning | UAT1 | 2024-01-19 | 2024-02-29 | 30 days |  |  | 0 day | 2024-01-19 | 2024-02-29 | 100 | 3 | 12;13+10d
12 | Tasks Properties (chargeble, type) | UAT1 | 2024-03-01 | 2024-03-14 | 10 days |  |  | 0 day | 2024-03-01 | 2024-03-14 | 100 | 11 | 14;15;26
13 | Project Size UC | UAT1 | 2024-03-15 | 2024-03-21 | 5 days |  |  | 0 day | 2024-03-15 | 2024-03-21 | 100 | 11+10d | 16FF
14 | Financial Widgets | UAT1 | 2024-03-15 | 2024-03-28 | 10 days |  |  | 0 day | 2024-03-15 |  | 70 | 12
15 | IC Loader | UAT1 | 2024-03-15 | 2024-03-28 | 10 days |  |  | 0 day | 2024-03-15 |  | 50 | 12 | 25;29
16 | Document Management | UAT1 | 2024-03-01 | 2024-03-28 | 20 days |  |  | 0 day | 2024-03-01 |  | 80 | 10;13FF
17 | Save Baseline | UAT1 | 2024-03-01 | 2024-03-28 | 20 days |  |  | 0 day | 2024-03-01 |  | 80 | 10
18 | 1st Release to AXA (Livetrial) | UAT1 | 2024-03-28 | 2024-03-28 | 0 days |  |  | 0 day |  |  | 0 |  | 23
19 | Functional GAPS UAT 1 - Demand Management | UAT1 | 2024-04-02 | 2024-04-08 | 5 days |  |  | 0 day |  |  | 0
20 | Analytics |  | 2024-03-18 | 2024-04-15 | 20 days |  |  | 0 day | 2024-03-18 |  | 10
21 | Custom Analytics Data Sources |  | 2024-03-18 | 2024-04-15 | 20 days |  |  | 0 day | 2024-03-18 |  | 10 |  | 31;52
22 | Integrations | UAT2 | 2024-03-28 | 2024-04-26 | 20 days |  |  | 0 day |  |  | 0
23 | APIs | UAT2 | 2024-03-28 | 2024-04-26 | 20 days |  |  | 0 day |  |  | 0 | 18 | 64
24 | Execution Management | UAT2 | 2024-03-01 | 2024-04-29 | 40 days |  |  | 0 day | 2024-03-01 |  | 15
25 | Import actuals (costs) | UAT2 | 2024-03-29 | 2024-04-12 | 10 days |  |  | 0 day |  |  | 0 | 15 | 31
26 | Activity Manager Role Implementation | UAT2 | 2024-03-15 | 2024-04-12 | 20 days |  |  | 0 day |  |  | 0 | 12 | 28;46
27 | BPM Data Table Active/Inactive records functionality | UAT2 | 2024-04-15 | 2024-04-29 | 10 days |  |  | 0 day |  |  | 0
28 | Status Update (costs label) | UAT2 | 2024-04-15 | 2024-04-29 | 10 days |  |  | 0 day |  |  | 0 | 26 | 31
29 | Vendor Time Tracking | UAT2 | 2024-03-29 | 2024-04-29 | 20 days |  |  | 0 day |  |  | 0 | 15 | 31
30 | New Resource Explorer Module | UAT2 | 2024-03-01 | 2024-04-29 | 40 days |  |  | 0 day | 2024-03-01 |  | 40 | 10 | 31
31 | 2nd Release to AXA (Livetrial) | UAT2 | 2024-04-30 | 2024-04-30 | 0 days |  |  | 0 day |  |  | 0 | 21;25;28;29;30;35 | 36;90
32 | Functional GAPS UAT 2 - Execution Management | UAT2 | 2024-05-03 | 2024-05-09 | 5 days |  |  | 0 day |  |  | 0
33 | Security |  | 2024-03-27 | 2024-05-15 | 33 days |  |  | 0 day |  |  | 0
34 | Financial data view permissions | UAT2 | 2024-04-16 | 2024-04-30 | 10 days |  |  | 0 day |  |  | 0 | 35FF
35 | Adjustments to Roles & Permissions (if any) | UAT2 | 2024-03-27 | 2024-04-30 | 23 days |  |  | 0 day |  |  | 0 | 58 | 31;34FF
36 | SSO - AD integration |  | 2024-05-02 | 2024-05-15 | 10 days |  |  | 0 day |  |  | 0 | 31 | 37;64
37 | 3rd Release to AXA (Livetrial) |  | 2024-05-15 | 2024-05-15 | 0 days |  |  | 0 day |  |  | 0 | 36 | 38
38 | Functional GAPS UAT 3 - Security & Integrations |  | 2024-05-16 | 2024-05-29 | 10 days |  |  | 0 day |  |  | 0 | 37
39 | Phase 03 - Solution Configuration |  | 2024-02-26 | 2024-06-10 | 73 days |  |  | 0 day | 2024-02-26 |  | 13
40 | Solution Configuration with standard features |  | 2024-02-26 | 2024-03-15 | 15 days |  |  | 0 day | 2024-02-26 |  | 93
41 | Business Objects Configuration |  | 2024-02-26 | 2024-03-01 | 5 days |  |  | 0 day | 2024-02-26 | 2024-03-01 | 100 |  | 42SS;43
42 | Roles Configuration |  | 2024-02-26 | 2024-03-01 | 5 days |  |  | 0 day | 2024-02-26 |  | 80 | 41SS | 44
43 | Forms Configuration |  | 2024-03-04 | 2024-03-08 | 5 days |  |  | 0 day | 2024-03-04 | 2024-03-08 | 100 | 41 | 44
44 | Workflows Configuration |  | 2024-03-11 | 2024-03-15 | 5 days |  |  | 0 day | 2024-03-11 |  | 90 | 42;43 | 57
45 | Solution Configuration with custom features |  | 2024-04-15 | 2024-05-07 | 15 days |  |  | 0 day |  |  | 0
46 | Additional Business Objects Configuration | UAT2 | 2024-04-15 | 2024-04-19 | 5 days |  |  | 0 day |  |  | 0 | 26 | 47SS;48
47 | Roles Configuration Refinement | UAT2 | 2024-04-15 | 2024-04-19 | 5 days |  |  | 0 day |  |  | 0 | 46SS
48 | Forms Configuration Refinement | UAT2 | 2024-04-22 | 2024-04-29 | 5 days |  |  | 0 day |  |  | 0 | 46 | 49
49 | Workflows Configuration Refinement |  | 2024-04-30 | 2024-05-07 | 5 days |  |  | 0 day |  |  | 0 | 48 | 61
50 | Email Notification (Timesheet & Baseline) |  | 2024-04-30 | 2024-05-07 | 5 days |  |  | 0 day |  |  | 0
51 | Dashboards |  | 2024-04-16 | 2024-06-10 | 38 days |  |  | 0 day |  |  | 0
52 | Implementation of DataSources based on SQL views |  | 2024-04-16 | 2024-05-29 | 30 days |  |  | 0 day |  |  | 0 | 21;63FF | 53SS;54SS;64
53 | Implementation of Reports |  | 2024-04-16 | 2024-05-29 | 30 days |  |  | 0 day |  |  | 0 | 52SS
54 | Implementation of Dashboards (1st Priority) |  | 2024-04-16 | 2024-06-10 | 38 days |  |  | 0 day |  |  | 0 | 52SS
55 | Phase 04 - Data Migrations |  | 2024-03-18 | 2024-06-17 | 63 days |  |  | 0 day | 2024-03-18 |  | 8
56 | Standard Data Migration (PO-Live->Uppwise Livetrial) |  | 2024-03-18 | 2024-04-03 | 12 days |  |  | 0 day | 2024-03-18 |  | 25
57 | Execution of standard migration scripts |  | 2024-03-18 | 2024-03-19 | 2 days |  |  | 0 day | 2024-03-18 | 2024-03-19 | 100 | 44 | 58
58 | Data verification |  | 2024-03-20 | 2024-03-26 | 5 days |  |  | 0 day | 2024-03-20 |  | 20 | 57 | 35;59
59 | Fine tuning of exceptions | UAT2 | 2024-03-27 | 2024-04-03 | 5 days |  |  | 0 day |  |  | 0 | 58
60 | Custom Data Migration (PO-Live->Uppwise Livetrial |  | 2024-05-08 | 2024-05-23 | 12 days |  |  | 0 day |  |  | 0
61 | Execution of standard migration scripts |  | 2024-05-08 | 2024-05-09 | 2 days |  |  | 0 day |  |  | 0 | 49 | 62
62 | Data verification |  | 2024-05-10 | 2024-05-16 | 5 days |  |  | 0 day |  |  | 0 | 61 | 63
63 | Fine tuning of exceptions |  | 2024-05-17 | 2024-05-23 | 5 days |  |  | 0 day |  |  | 0 | 62 | 52FF
64 | 4th Release to AXA (Livetrial) |  | 2024-05-29 | 2024-05-29 | 0 days |  |  | 0 day |  |  | 0 | 23;36;52 | 65
65 | Functional GAPS UAT 4 - Full Solution |  | 2024-05-30 | 2024-06-12 | 10 days |  |  | 0 day |  |  | 0 | 64 | 77+2d;78+2d;79+2d;80+2d;81+2d;82+2d;83+2d;84+2d;85+2d;86+2d;87+2d;88+2d
66 | Functional GAPS UAT 4 Dashboard Acceptance (Priority 1) |  | 2024-06-12 | 2024-06-17 | 4 days |  |  | 0 day |  |  | 0
67 | Phase 05 - Deployment & Go-Live |  | 2024-05-02 | 2024-07-09 | 49 days |  |  | 0 day |  |  | 0
68 | Production Setup for Go-Live |  | 2024-05-02 | 2024-05-22 | 15 days |  |  | 0 day |  |  | 0
69 | Solution Configuration - AXA Instance Setup PROD |  | 2024-05-02 | 2024-05-08 | 5 days |  |  | 0 day |  |  | 0 |  | 70;72;73
70 | Import Configuration DB from Uppwise Livetrial to PROD |  | 2024-05-09 | 2024-05-15 | 5 days |  |  | 0 day |  |  | 0 | 69 | 71
71 | Production Data Import - From PO Live to Uppwise PROD |  | 2024-05-16 | 2024-05-22 | 5 days |  |  | 0 day |  |  | 0 | 70
72 | Integration |  | 2024-05-09 | 2024-05-22 | 10 days |  |  | 0 day |  |  | 0 | 69
73 | Security |  | 2024-05-09 | 2024-05-22 | 10 days |  |  | 0 day |  |  | 0 | 69
74 | Ready to Go-Live |  | 2024-06-27 | 2024-06-27 | 0 days |  |  | 0 day |  |  | 0 | 75;78;92 | 95
75 | Parallel Running & Monitoring |  | 2024-06-10 | 2024-06-27 | 14 days |  |  | 0 day |  |  | 0 |  | 74
76 | PILOT Training |  | 2024-06-10 | 2024-06-14 | 5 days |  |  | 0 day |  |  | 0
77 | Business PM |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
78 | Continuos Fine Tuning |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d | 74
79 | Data PM |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
80 | Data Resource Manager |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
81 | Data Time Tracker |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
82 | Demand User |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
83 | IT BRM |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
84 | IT External Time Tracker |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
85 | IT PM |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
86 | IT Resource Manager |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
87 | IT Time Tracker |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
88 | Supplier Time Tracker |  | 2024-06-17 | 2024-06-27 | 9 days |  |  | 0 day |  |  | 0 | 65+2d
89 | Training |  | 2024-05-02 | 2024-06-27 | 41 days |  |  | 0 day |  |  | 0
90 | Tailored Training/Help |  | 2024-05-02 | 2024-05-30 | 21 days |  |  | 0 day |  |  | 0 | 31 | 91
91 | Train the trainer |  | 2024-05-31 | 2024-06-13 | 10 days |  |  | 0 day |  |  | 0 | 90 | 92
92 | Users Training |  | 2024-06-14 | 2024-06-27 | 10 days |  |  | 0 day |  |  | 0 | 91 | 74
93 | Go-Live Readiness |  | 2024-06-28 | 2024-07-04 | 5 days |  |  | 0 day |  |  | 0
94 | Go-Live Preparation Completed |  | 2024-07-04 | 2024-07-04 | 0 days |  |  | 0 day |  |  | 0 | 95 | 97;98
95 | Import Configuration DB from Uppwise Livetrial to PROD |  | 2024-06-28 | 2024-07-04 | 5 days |  |  | 0 day |  |  | 0 | 74 | 94
96 | Go-Live |  | 2024-07-05 | 2024-07-09 | 3 days |  |  | 0 day |  |  | 0
97 | Go-Live (System Unavailable) |  | 2024-07-05 | 2024-07-08 | 2 days |  |  | 0 day |  |  | 0 | 94 | 99
98 | Production Data Import - From PO Live to Uppwise PROD |  | 2024-07-05 | 2024-07-08 | 2 days |  |  | 0 day |  |  | 0 | 94
99 | System Live |  | 2024-07-09 | 2024-07-09 | 1 day |  |  | 0 day |  |  | 0 | 97
100 | Phase 06 - Dashboard Release |  | 2024-08-08 | 2024-11-29 | 79 days |  |  | 0 day |  |  | 0
101 | Release of Dashboards (2nd Priority) |  | 2024-08-08 | 2024-08-08 | 0 days |  |  | 0 day |  |  | 0
102 | Release of Dashboards (3rd Priority) |  | 2024-09-09 | 2024-09-09 | 0 days |  |  | 0 day |  |  | 0
103 | Release of Dashboards (4th Priority) |  | 2024-11-29 | 2024-11-29 | 0 days |  |  | 0 day |  |  | 0